## Sheet1
Task Name | Duration | Start | Finish
Motivation Monitor | 46 days | Mon 27/08/18 | Mon 29/10/18
First Sprint | 14 days | Mon 27/08/18 | Thu 13/09/18
Design 1 | 3 days | Mon 27/08/18 | Wed 29/08/18
Front End Design 1 | 1 day | Mon 27/08/18 | Mon 27/08/18
Mockups | 1 day | Mon 27/08/18 | Mon 27/08/18
Wireframing | 1 day | Mon 27/08/18 | Mon 27/08/18
Back End Design 1 | 2 days | Tue 28/08/18 | Wed 29/08/18
Use Cases | 2 days | Tue 28/08/18 | Wed 29/08/18
Class Diagrams | 2 days | Tue 28/08/18 | Wed 29/08/18
Database design | 2 days | Tue 28/08/18 | Wed 29/08/18
Coding 1 | 7 days | Thu 30/08/18 | Fri 7/09/18
Front End Coding 1 | 2 days | Wed 29/08/18 | Thu 30/08/18
GUI | 2 days | Wed 29/08/18 | Thu 30/08/18
Back End Coding 1 | 7 days | Wed 29/08/18 | Thu 6/09/18
Button functionality | 3 days | Fri 31/08/18 | Tue 4/09/18
Data logic | 4 days | Mon 3/09/18 | Thu 6/09/18
Testing 1 | 5 days | Fri 7/09/18 | Thu 13/09/18
Usability testing | 1 day | Fri 7/09/18 | Fri 7/09/18
Functionality testing | 1 day | Mon 10/09/18 | Mon 10/09/18
Unit testing | 1 day | Tue 11/09/18 | Tue 11/09/18
Integration testing | 1 day | Wed 12/09/18 | Wed 12/09/18
Performance testing | 1 day | Thu 13/09/18 | Thu 13/09/18
Second Sprint | 14 days | Fri 14/09/18 | Wed 3/10/18
Design 2 | 3 days | Fri 14/09/18 | Tue 18/09/18
Front End Design 2 | 1 day | Fri 14/09/18 | Fri 14/09/18
Mockups | 1 day | Fri 14/09/18 | Fri 14/09/18
Wireframing | 1 day | Fri 14/09/18 | Fri 14/09/18
Back End Design 2 | 2 days | Mon 17/09/18 | Tue 18/09/18
Use Cases | 2 days | Mon 17/09/18 | Tue 18/09/18
Class Diagrams | 2 days | Mon 17/09/18 | Tue 18/09/18
Database design | 2 days | Mon 17/09/18 | Tue 18/09/18
Coding 2 | 7 days | Wed 19/09/18 | Thu 27/09/18
Front End Coding 2 | 2 days | Wed 19/09/18 | Thu 20/09/18
GUI | 2 days | Wed 19/09/18 | Thu 20/09/18
Back End Coding 2 | 7 days | Fri 21/09/18 | Mon 1/10/18
Button functionality | 3 days | Fri 21/09/18 | Tue 25/09/18
Data logic | 4 days | Mon 24/09/18 | Thu 27/09/18
Testing 2 | 5 days | Fri 28/09/18 | Thu 4/10/18
Usability testing | 1 day | Mon 1/10/18 | Mon 1/10/18
Functionality testing | 1 day | Tue 2/10/18 | Tue 2/10/18
Unit testing | 1 day | Wed 3/10/18 | Wed 3/10/18
Integration testing | 1 day | Tue 4/09/18 | Tue 4/09/18
Performance testing | 1 day | Wed 5/09/18 | Wed 5/09/18
Third Sprint | 14 days | Fri 5/10/18 | Wed 24/10/18
Design 3 | 3 days | Fri 5/10/18 | Tue 9/10/18
Front End Design 3 | 1 day | Fri 5/10/18 | Fri 5/10/18
Mockups | 1 day | Fri 5/10/18 | Fri 5/10/18
Wireframing | 1 day | Fri 5/10/18 | Fri 5/10/18
Back End Design 3 | 2 days | Mon 8/10/18 | Tue 9/10/18
Use Cases | 2 days | Mon 8/10/18 | Tue 9/10/18
Class Diagrams | 2 days | Mon 8/10/18 | Tue 9/10/18
Database design | 2 days | Mon 8/10/18 | Tue 9/10/18
Coding 3 | 7 days | Wed 10/10/18 | Thu 18/10/18
Front End Coding 3 | 2 days | Wed 10/10/18 | Thu 11/10/18
GUI | 2 days | Wed 10/10/18 | Thu 11/10/18
Back End Coding 3 | 5 days | Fri 12/10/18 | Thu 18/10/18
Button functionality | 5 days | Fri 12/10/18 | Thu 18/10/18
Data logic | 5 days | Fri 12/10/18 | Thu 18/10/18
Testing 3 | 5 days | Fri 19/10/18 | Thu 25/10/18
Usability testing | 1 day | Fri 19/10/18 | Fri 19/10/18
Functionality testing | 1 day | Mon 22/10/18 | Mon 22/10/18
Unit testing | 1 day | Tue 23/10/18 | Tue 23/10/18
Integration testing | 1 day | Wed 24/10/18 | Wed 24/10/18
Performance testing | 1 day | Thu 25/10/18 | Thu 25/10/18
Integration/ Finalization | 3 days | Fri 26/10/18 | Tue 30/10/18
Publish To App Store | 1 day | Fri 26/10/18 | Fri 26/10/18
Create User Documentation | 2 days | Fri 26/10/18 | Mon 29/10/18
Install App On Devices | 1 day | Fri 26/10/18 | Fri 26/10/18
Complete Staff training | 1 day | Mon 29/10/18 | Mon 29/10/18